## Cover sheet
Version | Status | Date | Author | Comments
v0.1 | Old | 2026-04-15 | Laura Hargrave | Revised with feedback from Martin Wells: utilization by practice and sub-proposition reference. Additionally added overview slide.
v0.2 | Old | 2026-04-27 | Alf Pendlebury | All fields reviewed and updates applied where necessary. Validators assigned to each KPI / measure, validation date field for each measure. Capability Summary updated. Notes section updated.
v0.3 | Old | 2026-04-27 | Alf Pendlebury | Added separate measure for Overall RAG status, redefined overall RAG criteria. Applied formatting / cosmetic changes.
v0.4 | Current | 2026-05-06 | Alf Pendlebury | Added new column "Release" to show in which release each a particular measure will be in (initial estimates & see Note 4). Updated metrics post validation review (Fin & Delivery). Added Cost RAG per project measure & Deals > 4 months in the pipeline. Added Deleted Metrics tab. Capability summary updated. Added Utilisation by Practice measures for Cyber Security, Apps & Development and OT practices.
Notes:
N1: Managed Services are excluded from all KPI's & measures in this catalogue. N2: This catalogue refers only to the UK & India only. N3: For the purpose of this catalogue, a project currently in delivery is referred to as an "active project." N4: Product release dates TBC

## Metric Catalogue
nxzen Portfolio Office ¦ Metric Definition Catalogue ¦ DRAFT — April 2026
| METRIC IDENTITY |  |  |  | DEFINITION |  |  | DATA & GOVERNANCE |  |  |  |  | CAPABILITY ASSESSMENT | [6 empty] | DASHBOARD |  |  | THRESHOLDS
Release | # | Metric Name | Category | Sub-Category | Description | Calculation / Formula | Data Source (Process) | Source System / Tool | Data Owner | Update Frequency | Unit / Format | Reporting Period | Current Capability (Y / N) | If YES — Current Process | If YES — Data Source(s) | If NO — Gap Description | If NO — Process to Implement | Priority to Implement | Target Date | Dashboard Section | KPI / Measure Owner | Notes / Assumptions | RAG Green Threshold | RAG Amber Threshold | RAG Red Threshold | Benchmark / Target | Validated By | Date | Comments / Q's
MVP | 1 | Active Projects | Portfolio Snapshot | Portfolio at a Glance | Total count of nxzen (UK & India) active projects | COUNT of active projects from the Dynamics Project extract | Active projects in Dynamics | Extract from Dynamics (link TBC) | Finance | Weekly | Count (#) | Current month | Y (partial) | Finance have a list of all projects | Extract from Dynamics | Would need to count only active projects (e.g. remove managed svcs, etc.) | Filter extract to only counts active projects | High |  | Portfolio Snapshot | Syed | Dormant or closed projects excluded. | N/A | N/A | N/A | N/A | Syed | 2026-05-01
MVP | 2 | Active Clients | Portfolio Snapshot | Portfolio at a Glance | Number of distinct (UK & India) clients with at least one active project | COUNT DISTINCT (Client) of active projects from the Dynamics Project extract | Active projects in Dynamics | Extract from Dynamics (link TBC) | Finance | Weekly | Count (#) | Current month | Y (partial) | Finance have a list of all projects | Extract from Dynamics shows customer (Client) | Would need to count only clients with a current active project(s) (e.g. remove managed svcs, etc.) | Filter extract to only counts clients with an active project(s) | High |  | Portfolio Snapshot | Syed | One client may have multiple projects; deduplicated count. | N/A | N/A | N/A | N/A | Syed | 2026-05-01
MVP | 3 | Overall RAG Status | Portfolio Snapshot | Portfolio at a Glance | Overall RAG status of the portfolio | If overall RAG Red %: ≥10% then Red If overall RAG Amber %:≥5%–<10% then Amber If overall RAG Green %: <5% Red or Amber, then Green | PM-reported RAG per project during weekly review | Acct Delivery Status Report: Milestone plan | PM (reported), Portfolio Office (validate & consolidate) | Weekly | % (one decimal) | Current week | Y (partial) | PMs self-report RAG per project / acct; Portfolio Office analyses each report, validates. No Portfolio / overall RAG | Acct delivery weekly reports (.PPT) | Currently no overall / portfolio RAG status | Need to apply portfolio / overall RAG criteria & apply for all active projects | High |  | Portfolio Snapshot | Syed | Overall RAG: Red: ≥10% Proj Red Overall RAG: Amber: Not Red & ≥5% Amber Overall RAG: Green: Not Red or Amber | <5% Red or Amber | ≥5%–<10% | ≥10% | Green | Syed | 2026-05-01
MVP | 4 | Overall RAG — Red % | Portfolio Snapshot | Portfolio at a Glance | Percentage of active projects with an overall RAG status of Red. | COUNT(Overall RAG = Red) / COUNT(Active Projects) × 100 | PM-reported RAG per project during weekly review | Acct Delivery Status Report: Milestone plan | PM (reported), Portfolio Office (validate & consolidate) | Weekly | % (one decimal) | Current week | Y (partial) | PMs self-report RAG per project / acct; Portfolio Office analyses each report, validates. No Portfolio / overall RAG | Acct delivery weekly reports (.PPT) | Currently no overall / portfolio RAG status | Need to apply portfolio / overall RAG criteria & apply for all active projects | High |  | Portfolio Snapshot | Syed | Overall RAG criteria: Red: ≥10% of projects are Red. | <5% Red or Amber | ≥5%–<10% | ≥10% | ≤3% red | Syed | 2026-05-01 | 1. Process to gather data is there, not being followed in all instances. 2. Notes / Assumptions Red criteria is for per account, not portfolio / overall RAG.
MVP | 5 | Overall RAG — Amber % | Portfolio Snapshot | Portfolio at a Glance | Percentage of active projects with an overall RAG status of Amber. | COUNT(Overall RAG = Amber) / COUNT(Active Projects) × 100 | PM-reported RAG per project during weekly review | Acct Delivery Status Report: Delivery status | PM (reported), Portfolio Office (validate & consolidate) | Weekly | % (one decimal) | Current week | Y (partial) | PMs self-report RAG per project / acct; Portfolio Office analyses each report, validates. No Portfolio / overall RAG | Acct delivery weekly reports (.PPT) | Currently no overall / portfolio RAG status | Need to apply portfolio / overall RAG criteria & apply for all active projects | High |  | Portfolio Snapshot | Syed | Overall RAG criteria: Amber: overall RAG is not Red & ≥5% of projects are Amber | <5% Red or Amber | ≥5%–<10% | ≥10% | ≤7% amber | Syed | 2026-05-01 | 1. Process to gather data is there, not being followed in all instances.
MVP | 6 | Overall RAG — Green % | Portfolio Snapshot | Portfolio at a Glance | Percentage of active projects with an overall RAG status of Green. | COUNT(Overall RAG = Green) / COUNT(Active Projects) × 100 | PM-reported RAG per project during weekly review | Acct Delivery Status Report: Delivery status | PM (reported), Portfolio Office (validate & consolidate) | Weekly | % (one decimal) | Current week | Y (partial) | PMs self-report RAG per project / acct; Portfolio Office analyses each report, validates. No Portfolio / overall RAG | Acct delivery weekly reports (.PPT) | Currently no overall / portfolio RAG status | Need to apply portfolio / overall RAG criteria & apply for all active projects | High |  | Portfolio Snapshot | Syed | Overall RAG criteria: Green: overall RAG is not Red or Amber | <5% Red or Amber | ≥5%–<10% | ≥10% | ≥90% green | Syed | 2026-05-01 | 1. Process to gather data is there, not being followed in all instances.
MVP | 7 | On Time % | Portfolio Snapshot | Delivery Indicators | Measures the next due milestone. Percentage of active projects tracking on schedule (On schedule RAG: Green = no slippage). | COUNT (Next due milestone RAG = Green) / COUNT (Active Projects) × 100 | PM provides milestone plan and actual progress weekly | Acct Delivery Status Report: Milestone plan | PM (reported), Portfolio Office (validate & consolidate) | Weekly | % (one decimal) | Current week | Y (partial) | PMs self-report milestones per project / acct; Portfolio Office analyses each report, validates. No Portfolio / overall % on time | Acct delivery weekly reports (.PPT) | No standard milestone tracking tool or format across all PMs. Schedule data not consolidated. | Define standard milestone template; PMs update weekly; Portfolio Office validates & consolidates at account review. Automate extraction via AI agent. | High | 01/06/2026 | Portfolio Snapshot | PM per project | RAG: Red = project has slipped. Amber = project at risk of slippage unless action is taken. Green = no slippage & no risk of slippage. Benchmark from current wireframe: 71% on-time. | ≥80% | 65–<80% | <65% | ≥80% | Syed | 2026-05-01
MVP | 8 | Projects Behind Schedule (count) | Portfolio Snapshot | Delivery Indicators | Measures the next due milestone. Count of active projects where schedule RAG: Red = next due milestone has slipped. | COUNT(Next due milestone RAG = Red) | PM provides milestone plan and actual progress weekly | Acct Delivery Status Report: Milestone plan | PM (reported), Portfolio Office (validate & consolidate) | Weekly | Count (#) | Current week | Y (partial) | PMs self-report milestones per project / acct; Portfolio Office analyses each report, validates. No Portfolio / overall behind schedule count | Acct delivery weekly reports (.PPT) | No standard milestone tracking tool or format across all PMs. Schedule data not consolidated. | Define standard milestone template; PMs update weekly; Portfolio Office validates & consolidates at account review. Automate extraction via AI agent. | High | 01/06/2026 | Portfolio Snapshot | PM per project | RAG: Red = project has slipped. Amber = project at risk of slippage unless action is taken. Green = no slippage & no risk of slippage. | N/A | N/A | N/A | N/A | Syed | 2026-05-01
REL 2 | 9 | On Budget % | Portfolio Snapshot | Delivery Indicators | Percentage of active projects, where forecast cost is in line with approved budget. (Budget RAG: Green = is in line with approved budget). | COUNT(Budget RAG = Green) / COUNT(Active Projects) × 100 | PM and Finance provide actual vs budget cost data | Finance system + PM budget tracker | Finance (actuals), PM (forecast) | Monthly (minimum) | % (one decimal) | Current month | N | Budget data held in Finance system but not linked to project register or dashboard. No standard budget tracker per project. |  | Actuals in Finance system; forecast held informally by PM. No single source. No automated consolidation. | Introduce standard project budget tracker (template). Finance to share actuals monthly. PM to update forecast. Portfolio Office to consolidate. | High | 01/06/2026 | Portfolio Snapshot | PM per project | RAG: Red = project is over budget. Amber = project at risk of going over budget unless action is taken. Green = not over budget & not at risk of going over. | ≥80% | 65–<80% | <65% | ≥80% | Syed | 2026-05-01
REL 2 | 10 | Projects Over Budget (count) | Portfolio Snapshot | Delivery Indicators | Count of active projects where forecast cost exceeds approved budget. | COUNT (Budget RAG = Red) | PM and Finance provide actual vs budget cost data | Finance system + PM budget tracker | Finance (actuals), PM (forecast) | Monthly | Count (#) | Current month | N | Budget data held in Finance system but not linked to project register or dashboard. No standard budget tracker per project. |  | Actuals in Finance system; forecast held informally by PM. No single source. No automated consolidation. | Introduce standard project budget tracker (template). Finance to share actuals monthly. PM to update forecast. Portfolio Office to consolidate. | High | 01/06/2026 | Portfolio Snapshot | PM per project | RAG: Red = project is over budget. Amber = project at risk of going over budget unless action is taken. Green = not over budget & not at risk of going over. | N/A | N/A | N/A | N/A | Syed | 2026-05-01
MVP | 11 | Resource Gaps Flagged | Portfolio Snapshot | Delivery Indicators | Count of active projects with a flagged resource gap (Resource RAG = Red or Amber). | COUNT(Resource RAG ∈ {Amber, Red}) | PM flags resource gaps at weekly account review | PM status update / resource plan | PM (flagged), Portfolio Office (consolidated) | Weekly | Count (#) | Current week | Y (partial) | PMs flag resource gaps verbally in account reviews. Not formally tracked or logged. | Verbal account review notes | Gaps flagged informally — no structured log or consistent criteria. | Add resource gap field to weekly PM status template. Log in project register. Alert Portfolio Office when flagged. | Medium | 01/05/2026 | Portfolio Snapshot | Resource Manager | RAG: Red = resource issue now / will miss schedule unless action is taken. Amber = will become a resource problem unless action is taken. Green = no resource issues | 0 | >0–<2 | ≥2 | 0 | Syed | 2026-05-01
REL 3 | 12 | Client Satisfaction Score | Portfolio Snapshot | Delivery Indicators | Percentage of clients rating project delivery ≥4/5 (or equivalent) in most recent satisfaction check. | COUNT(CSAT ≥4) / COUNT(CSAT responses) × 100 | Client satisfaction survey or conversation-based check with CP | Survey tool or structured CP debrief | TBC (a Corporate owner is required) | Monthly / per milestone | % (one decimal) | Last 30 days or last survey round | N | No formal client satisfaction process or survey tool in place. |  | CSAT not systematically collected. CPs have informal client sentiment but no structured data. | Define lightweight CSAT process (1–5 rating + comment at milestone/monthly). CP collects and logs. Portfolio Office aggregates. | High | 01/06/2026 | Portfolio Snapshot | TBC (a Corporate owner is required) | Benchmark from wireframe: 69%. A Corporate owner is required for this measure so as to be independent of the sales / delivery function | ≥90% | 60–<90% | <60% | ≥90% | TBC | 2026-05-01 | I think the green should be ≥90% similar measure for NPS (9 & 10 - promoters, whereas 8 (80%) would be passives, indicates our clients are indifferent to us)
MVP | 13 | Utilisation – UK (overall) | Resource & Utilisation | Overall | Percentage of billable & business/practice developmenthours worked against available billable & internal project capacity for UK-based resources. | Billable & business/practice development (hours) logged / Available billable & internal project hours (contracted − leave) × 100 | Timesheets submitted weekly by all UK resources | Dynamics Timesheets BI | Resource Manager / Finance | Weekly | % (one decimal) | Current week / rolling 4-week avg | Y (partial) | Timesheets saved weekly. BI report can separate UK & IN users. | Dynamics Timesheets | Currently report on current / past week & month not rolling 4 weeks Need to confirm the calculation with Saurabh | Build automated utilisation calculation from timesheet data; surface weekly in dashboard. | Medium | 01/05/2026 | Portfolio Snapshot | Resource Manager | Target 82% billable utilisation. | ≥82% | 70–<82% | <70% | 82% | Syed | 2026-05-01 | Can we review the calculation in Timesheets (BI), to fit our need here
MVP | 14 | Utilisation – India (overall) | Resource & Utilisation | Overall | Percentage of billable & business/practice development hours worked against available billable & internal project capacity for India-based resources. | Billable & business/practice development (hours) logged / Available billable & internal project hours (contracted − leave) × 100 | Timesheets submitted weekly by India resources | Dynamics Timesheets BI | Resource Manager / India Resource Lead | Weekly | % (one decimal) | Current week / rolling 4-week avg | Y (partial) | Timesheets saved weekly. BI report can separate UK & IN users. | Dynamics Timesheets | Currently report on current / past week & month not rolling 4 weeks Need to confirm the calculation with Saurabh | Build automated utilisation calculation from timesheet data; surface weekly in dashboard. | High | 01/06/2026 | Portfolio Snapshot | India Resource Lead | Target 82% billable utilisation. | ≥82% | 70–<82% | <70% | 82% | Syed | 2026-05-01 | Timesheet data entry and BI reports are one and the same for UK & India (unless something has changed) so in theory one fix will suffice for both areas (and AU/NZ when their time comes)
REL 2 | 15 | Utilisation – by Practice (Renewables & Eng) | Resource & Utilisation | By Practice | Percentage of billable & business/practice development utilisation for resources aligned to the Renewables & Engineering practice/sub-proposition. | Billable & ibusiness/practice development hours logged (Renewables & Eng resources) / Available billable hours (same group) × 100 | Timesheets submitted weekly by all UK & India resources | Dynamics Timesheets BI | Practice Lead / Resource Manager | Weekly | % (one decimal) | Current week | N |  |  | No practice-level tagging in timesheet or resource data. Cannot slice utilisation by practice. | Tag all resources with practice/sub-proposition in resource system. Build grouping logic in dashboard. | High | 01/06/2026 | Portfolio Snapshot | Practice Lead | Practices: Renewables & Eng ¦ Data Intelligence & AI ¦ Cyber ¦ Apps & Dev ¦ OT. | ≥82% | 70–<82% | <70% | 82% | Syed | 2026-05-01
REL 2 | 16 | Utilisation – by Practice (Data Intelligence & AI) | Resource & Utilisation | By Practice | Percentage of billable & business/practice development utilisation for resources aligned to the Data Intelligence & AI practice. | Billable & business/practice development hours logged (Data Intelligence & AI) / Available billable hours (same group) × 101 | Timesheets submitted weekly by all UK & India resources | Dynamics Timesheets BI | Practice Lead / Resource Manager | Weekly | % (one decimal) | Current week | N |  |  | No practice-level tagging in timesheet or resource data. Cannot slice utilisation by practice. | Tag all resources with practice/sub-proposition in resource system. Build grouping logic in dashboard. | High | 01/06/2026 | Portfolio Snapshot | Practice Lead |  | ≥82% | 70–<82% | <70% | 82% | Syed | 2026-05-01
REL 2 | 17 | Utilisation – by Practice (Cyber Security) | Resource & Utilisation | By Practice | Percentage of billable & business/practice development utilisation for resources aligned to the Cyber Security practice/sub-proposition. | Billable & ibusiness/practice development hours logged (Cyber Security resources) / Available billable hours (same group) × 100 | Timesheets submitted weekly by all UK & India resources | Dynamics Timesheets BI | Practice Lead / Resource Manager | Weekly | % (one decimal) | Current week | N |  |  | No practice-level tagging in timesheet or resource data. Cannot slice utilisation by practice. | Tag all resources with practice/sub-proposition in resource system. Build grouping logic in dashboard. | High | 01/06/2026 | Portfolio Snapshot | Practice Lead | Practices: Renewables & Eng ¦ Data Intelligence & AI ¦ Cyber ¦ Apps & Dev ¦ OT. | ≥82% | 70–<82% | <70% | 82% | Syed | 2026-05-01
REL 2 | 18 | Utilisation – by Practice (Apps & Development) | Resource & Utilisation | By Practice | Percentage of billable & business/practice development utilisation for resources aligned to the Aps & Development practice/sub-proposition. | Billable & ibusiness/practice development hours logged (Apps & Development resources) / Available billable hours (same group) × 100 | Timesheets submitted weekly by all UK & India resources | Dynamics Timesheets BI | Practice Lead / Resource Manager | Weekly | % (one decimal) | Current week | N |  |  | No practice-level tagging in timesheet or resource data. Cannot slice utilisation by practice. | Tag all resources with practice/sub-proposition in resource system. Build grouping logic in dashboard. | High | 01/06/2026 | Portfolio Snapshot | Practice Lead | Practices: Renewables & Eng ¦ Data Intelligence & AI ¦ Cyber ¦ Apps & Dev ¦ OT. | ≥82% | 70–<82% | <70% | 82% | Syed | 2026-05-01
REL 2 | 19 | Utilisation – by Practice (OT) | Resource & Utilisation | By Practice | Percentage of billable & business/practice development utilisation for resources aligned to the OT practice/sub-proposition. | Billable & ibusiness/practice development hours logged (OT resources) / Available billable hours (same group) × 100 | Timesheets submitted weekly by all UK & India resources | Dynamics Timesheets BI | Practice Lead / Resource Manager | Weekly | % (one decimal) | Current week | N |  |  | No practice-level tagging in timesheet or resource data. Cannot slice utilisation by practice. | Tag all resources with practice/sub-proposition in resource system. Build grouping logic in dashboard. | High | 01/06/2026 | Portfolio Snapshot | Practice Lead | Practices: Renewables & Eng ¦ Data Intelligence & AI ¦ Cyber ¦ Apps & Dev ¦ OT. | ≥82% | 70–<82% | <70% | 82% | Syed | 2026-05-01
MVP | 20 | Unassigned Resources % | Resource & Utilisation | Capacity | Percentage of total UK & India resource headcount currently unassigned to any active project. | COUNT(Unassigned FTE excl. Corporate) / Total FTE (excl. Corporate) × 100 | Timesheets submitted weekly by all UK & India resources | Dynamics Timesheets BI | Resource Manager | Weekly | % (one decimal) | Current week | Y | Users log time and select "Type" "unassigned" | Dynamics Timesheets |  |  | High | 01/06/2026 | Portfolio Snapshot | Resource Manager | Benchmark: 11%. | ≤10% | >10–≤20% | >20% | ≤10% | Syed | 2026-05-01
MVP | 21 | Unbillable Resources % | Resource & Utilisation | Capacity | Percentage of total UK & India hours logged against non-billable codes (internal, bench, training). | Non-billable hours (excl. Corporate) / Total logged hours (excl. Corporate) × 100 | Timesheet data — hours logged to non-billable project codes | Dynamics Timesheets BI | Finance / Resource Manager | Weekly | % (one decimal) | Current week / rolling 4-week | Y | Users log time against "Type" & "Project" | Dynamics Timesheets |  |  | Medium | 01/05/2026 | Portfolio Snapshot | Finance | Benchmark: 26%. Includes bench time, internal projects, training. | ≤15% | >15–25% | >25% | ≤15% | Syed | 2026-05-01
MVP | 22 | Schedule RAG per Project | Delivery Health | Project Status | Measures the project as a whole. Schedule performance for each active project rated Green/Amber/Red against defined criteria. | Green: no slippage; Amber: risk of slippage if no action taken Red project has slipped. | PM provides milestone actuals vs baseline at weekly account review | Project plan (standardised template) | PM | Weekly | RAG (G/A/R) | Current week | Y (partial) |  |  | Each PM uses different tools (Excel, MS Project, Jira). No baseline plan consistently maintained. | Mandate standard milestone plan template. PMs update weekly. RAG auto-calculated. Portfolio Office reviews in account review. | High | 01/06/2026 | Delivery Health | PM per project | RAG: Red = project has slipped. Amber = project at risk of slippage unless action is taken. Green = no slippage & no risk of slippage. | ≤5% slip | >5–15% slip | >15% slip | Green | Syed | 2026-05-01
REL 2 | 23 | Target Margin RAG per Project | Delivery Health | Project Status | Target margin performance for each active project rated against approved budget. | Green <2% variance; Amber 2–5% variance; Red >5% variance | Finance actuals + PM forecast submitted monthly (minimum) or at milestone | Finance system + PM budget tracker | Finance (actuals), PM (forecast) | Monthly | RAG (G/A/R) | Current month | N |  |  | Actuals in Finance system; forecast held informally by PM. No single source. No automated consolidation. | Introduce standard project budget tracker (template). Finance to share actuals monthly. PM to update forecast. Portfolio Office to consolidate. | High | 01/06/2026 | Delivery Health | PM per project |  | <2% | 2–5% | >5% | Green | Sarah B | 2026-05-01
MVP | 24 | Resource RAG per Project | Delivery Health | Project Status | Resource health per active project. RAG: Red = resource issue now / will miss schedule unless action is taken. Amber = will become a resource problem unless action is taken. Green = no resource issues | PM assessment against role/skill requirement plan vs actuals. | PM assessment at weekly account review | PM status update | PM | Weekly | RAG (G/A/R) | Current week | Y (partial) | PMs informally assess resource health. Not formally documented or logged against criteria. | Verbal PM update | No formal resource requirement plan per project to compare against. | Define standard resource plan template per project. PM assesses weekly against criteria. Log in project register. | Medium | 01/05/2026 | Delivery Health | PM per project |  | No resource issues | Become resource issue unless action taken | Is a resource issue. Schedule missed if no action taken | Green | Syed | 2026-05-01
REL 2 | 25 | Scope RAG per Project | Delivery Health | Project Status | Scope stability per active project: Green = baseline approved and stable; Amber = changes identified not yet agreed; Red = uncontrolled scope change impacting T/C/Q. | PM assessment against agreed scope baseline. | PM reports scope status at account review | Project scope document + change log | PM | Weekly | RAG (G/A/R) | Current week | N | Change log and scope baseline not maintained consistently across projects. |  | No standard change log or scope baseline documentation per active project. | Mandate scope baseline document and change log per active project. PM updates weekly. RAG assessed against criteria. | High | 01/06/2026 | Delivery Health | PM per project |  | Stable / approved | Change identified not yet agreed | Uncontrolled change | Green | Syed | 2026-05-01
MVP | 26 | Open Risks per Project | Delivery Health | Risks & Issues | Count and detail of open risks per active project, categorised by rating and status. | COUNT(Risks where Status = Open), grouped by active project and severity. | PM-maintained risk register updated weekly | Risk register (standardised template) | PM | Weekly | Count + detail | Current week | Y (partial) | Risk logs exist informally per PM but no standard format and no consolidated view. |  | No standard risk register template or consolidated risk log. No consistent severity rating scale. | Define standard risk register template with probability/impact scoring. PMs update weekly. Portfolio Office consolidates and surfaces High risks. | High | 01/06/2026 | Delivery Health | PM per project | Risk Assessment Aid | N/A | N/A | N/A | N/A | Syed | 2026-05-01 | Displayed in Top Risks & Issues log on dashboard.
MVP | 27 | Open Issues per Project | Delivery Health | Risks & Issues | Count and detail of open issues (materialised risks or blockers) per active project. | COUNT(Issues where Status = Open), grouped by active project. | PM-maintained issue log updated weekly | Issue log (standardised template) | PM | Weekly | Count + detail | Current week | Y (partial) | Issues not formally tracked. Raised verbally in account reviews but not logged. |  | No standard issue log. Issues not differentiated from risks. | Define and mandate issue log (separate from risk log). PMs update weekly. Portfolio Office consolidates. | High | 01/06/2026 | Delivery Health | PM per project | Displayed in Top Risks & Issues log on dashboard. | N/A | N/A | N/A | N/A | Syed | 2026-05-01
REL 1 | 28 | Total Portfolio Value | Commercial | Revenue | Sum of contracted value of all active projects. | SUM(Contracted Value) across all active projects. | Contracts signed; value entered into Zen X by Cpthen entered into Finance spreadsheets | Finance system / Excel spreadsheets | Finance / Client Partner | On contract signature (updated monthly) | £ (GBP, thousands) | Cumulative active portfolio | Y | Existing Finance process included in the Month End pack | Zen X + Finance system |  |  | Medium | 01/05/2026 | Commercial | Growth | Benchmark: £4.2M. | N/A | N/A | N/A | N/A | Sarah B | 2026-05-01
REL 1 | 29 | Revenue Recognised MTD | Commercial | Revenue | Revenue formally recognised in the current month to date, per accounting policy. | SUM(Revenue Recognised) where recognition date in current calendar month. | Finance team applies revenue recognition and updates monthly | Finance / Accounting system | Finance | Monthly | £ (GBP, thousands) | Month to date | Y | Finance recognises revenue monthly per project. Data exists but not surfaced in dashboard. | Finance accounting system & spreadsheets |  |  | Medium |  | Commercial | Growth | Finance | Benchmark: £1.1M MTD. Show vs plan variance. | N/A | N/A | N/A | Sarah B | 2026-05-01
REL 1 | 30 | Revenue vs Plan Variance | Commercial | Revenue | Difference between actual revenue recognised MTD and planned revenue for the month. | Revenue Recognised MTD − Revenue Plan MTD. Show as £ and %. | Finance actuals vs revenue plan (set at project kick-off or annual plan) | Finance system + revenue plan | Finance | Monthly (ideally weekly) | £ and % | Month to date | Y | Existing Finance process included in the Month End pack | Finance accounting system & spreadsheets |  | Finance to produce monthly revenue plan at project level. Portfolio Office consolidates. Compare to actuals monthly. | High | 01/06/2026 | Commercial | Finance | Benchmark: ▲£140k vs plan. | N/A | N/A | N/A | N/A | Sarah B | 2026-05-01
REL 1 | 31 | Average Project Margin % | Commercial | Margin | Average gross margin across all active projects (revenue minus direct delivery cost). | AVERAGE(Project Margin %) where Margin = (Revenue − Direct Costs) / Revenue × 100. | Finance calculates margin per project from timesheet costs + expenses vs recognised revenue | Finance system | Finance | Monthly | % (one decimal) | Current month | Y | Existing Finance process included in the Month End pack | Finance accounting system & spreadsheets |  | Finance to produce per-project margin statement monthly. Portfolio Office aggregates. Dashboard shows average and per-project. | High | 01/06/2026 | Commercial | Growth | Target: 35%. Benchmark: 31%. | ≥35% | 28–<35% | <28% | ≥35% | Sarah B | 2026-05-01
MVP | 32 | Billable Utilisation % | Commercial | Margin | Percentage of total logged hours that are billable to a client — commercial lens on utilisation. | Billable hours / Total hours logged (excl. Corporate) × 100 (all resources, UK + India). | Timesheet data — hours logged to billable project codes | Dynamics Timesheets BI | Finance / Resource Manager | Weekly | % (one decimal) | Current week / rolling 4-week | Y (partial) | Timesheets saved weekly. BI report can separate UK & IN users. | Dynamics Timesheets |  |  | High |  | Commercial | Growth | Finance. Benchmark 78% | ≥82% | <82-70% | <70% | ≥82% | Syed | 2026-05-01
REL 2 | 33 | Win Rate (6-month rolling) | Commercial | Pipeline | Percentage of pitched opportunities won in the rolling 6-month window. | COUNT(Opportunities Won) / COUNT(Opportunities Pitched) × 100 over rolling 6 months. | CPs log pitches and outcomes in Zen X | Zen X | Client Partner / Growth team (Mike Farrell) | Monthly | % (one decimal) | Rolling 6 months | N | Win/loss data not consistently logged in Zen X. Tracked informally by CPs. |  | Pitches and outcomes not systematically recorded. No Zen X discipline enforced. | Mandate CP updates Zen X at each stage: pitched, won, lost. Define 'pitched' (formal proposal submitted). Portfolio Office extracts monthly. | High | 01/06/2026 | Commercial | Client Partner | Benchmark: 44% (5 won of 11 pitched). | ≥50% | 35–<50% | <35% | ≥50% | Mike | 2026-05-01
REL 2 | 34 | Pipeline Value | Commercial | Pipeline | Total value of opportunities currently in pipeline from Prospect to Negotiation stage. | SUM(Opportunity Value) where Stage ∈ {Prospect, Qualified, Proposal, Negotiation}. | CPs maintain pipeline in Zen X | Zen X | Client Partner / Growth team (Mike Farrell) | Weekly | £ (GBP, thousands) | Current snapshot | N | Zen X not consistently used by all CPs. Pipeline values not reliably maintained. |  | Zen X hygiene is inconsistent. Pipeline value not a reliable source of truth. | Enforce Zen X pipeline hygiene standard. Weekly CP pipeline review. Portfolio Office extracts pipeline value each Friday. | High | 01/06/2026 | Commercial | Client Partner | Benchmark: £3.35M. Scope: Prospect to Negotiation. | N/A | N/A | N/A | N/A | Mike | 2026-05-01
REL 2 | 35 | Repeat Business Rate % | Commercial | Pipeline | Percentage of revenue (or active projects) in the current period derived from existing clients (re-contracted or extended). | Revenue (or active projects) from existing clients (renewed/extended) / Total Revenue × 100. | CP identifies new vs repeat at project initiation. Finance validates against client history. | Zen X + Finance | Client Partner | Monthly | % (one decimal) | Rolling 12 months or current period | N | Repeat vs new business not formally categorised in Zen X or Finance. |  | No field in Zen X or project register to flag new vs repeat client engagement. | Add New vs Repeat flag to project register and Zen X. CP confirms at kick-off. Finance validates. | Medium | 2026-06-01 | Commercial | Client Partner | Target: 60%. Benchmark: 68%. | ≥60% | 50–<60% | <50% | ≥60% | Mike | 2026-05-01
REL 2 | 36 | Average Days to Contract | Commercial | Pipeline | Average number of calendar days from opportunity creation/bid submission to signed contract. | AVERAGE(Contract Signed Date − Opportunity Created/Bid Submitted Date) across deals closed in period. | CPs log opportunity creation and contract dates in Zen X | Zen X | Client Partner / Legal | Monthly | Days (whole number .5 or > rolled up) | Rolling 3-month average | N | Contract dates not consistently logged in Zen X. Legal/procurement cycle not tracked. |  | No systematic tracking of bid-to-contract timeline. | Log bid submission date and contract signed date in Zen X for all opportunities. Calculate automatically. | Medium | 2026-06-01 | Commercial | Client Partner | Target: 20 days. Benchmark: 23 days. | ≤20 days | >20–30 days | >30 days | ≤20 days | Mike | 2026-05-01
REL 3 | 37 | Planned vs Actual Invoicing | Commercial | Invoicing | Variance between the invoices planned to be raised in the period and the invoices actually raised. Measures billing discipline and cash flow predictability. | Planned Invoice Value (period) − Actual Invoice Value (period). Express as £ variance and % variance: (Actual − Plan) / Plan × 100. Report at project level and portfolio total. | Invoice schedule set at active project kick-off by CP/Finance. Actuals pulled from Finance/accounting system after month-end close. | Finance / Accounting system (e.g. Xero, SAP, NetSuite) + Invoice schedule (project register or Finance tracker) | Finance | Monthly | £ (GBP) and % variance — shown per project and portfolio total | Current month / rolling quarter | N |  |  | No invoice schedule is formally documented at project level. Invoicing is tracked in the Finance system but not compared against a planned schedule. No consolidated portfolio-level invoicing view exists. | 1. Mandate CP/Finance to document an invoice schedule (date, milestone trigger, expected value) at active project kick-off. 2. Finance records actuals in the same tracker post-invoice. 3. Portfolio Office consolidates monthly. 4. Surface planned vs actual in dashboard with RAG: Green ≤±5%, Amber 6–15%, Red >15% or invoice missed entirely. | High | 01/06/2026 | Commercial | Finance | Distinct from Revenue Recognised (metric #26/#27) — invoicing is a cash/billing event; revenue recognition follows accounting policy and may differ in timing. Both metrics are needed. A missed invoice does not equal unrecognised revenue but does signal cash flow and delivery milestone risk. | ≤±5% variance | >5–15% variance or 1 invoice delayed | >15% variance or invoice missed entirely | 0% variance (invoice on time, full value) | Sarah B | 2026-05-01
REL 1 | 38 | Gross Margin £ (per project and portfolio) | Commercial | Margin | Absolute gross margin in pounds (£) for each active project and the portfolio total. Gross margin = Revenue − Direct Delivery Cost. Complements metric #28 (Average Project Margin %) by providing the £ value, enabling prioritisation by commercial impact rather than percentage alone. A project with a high margin % but low £ value may be less commercially significant than a lower-% but higher-value project. | Gross Margin £ = Revenue Recognised − Direct Delivery Cost. Direct Delivery Cost = Labour Cost (billable hours × cost rate) + Direct Expenses (travel, subcontractors, software, etc.). Portfolio Gross Margin £ = SUM(Gross Margin £) across all active projects. Gross Margin % (cross-reference) = Gross Margin £ / Revenue Recognised × 100. | Revenue from Finance (recognised per accounting policy). Direct costs: labour from timesheets × internal cost rates; expenses from Finance expense system. Finance produces per-project P&L statement monthly. | Finance / Accounting system (revenue + costs) + Dynamics Timesheet BI (labour hours) + Expense management system | Finance | Monthly | £ (GBP, thousands) — shown per project; portfolio total; with Gross Margin % alongside | Current month and cumulative to date; forecast to project completion | Y |  | Finance accounting system & spreadsheets |  |  | High | 01/06/2026 | Commercial | Finance | Gross margin excludes indirect costs (overhead, sales, G&A). It is a project-level delivery margin, not a company P&L net margin. Internal cost rates must be agreed and locked for a period (e.g. annually) to ensure comparability month-on-month. Subcontractor costs are a direct cost and must be included. Do not confuse with margin target set at bid stage — report both bid margin and actual margin to track erosion. | Gross Margin % ≥35% (and £ above project-level minimum threshold) | Gross Margin % 28–<35% | Gross Margin % <28% or £ gross margin negative | Gross Margin % ≥35% per project; portfolio total gross margin maximised | Sarah B | 2026-05-01
MVP | 39 | Escalations and decisions required per project | Delivery Health | Project Status | All escalations and decisions required per project, monitored on a weekly basis | All escalations and decisions required per project, monitored on a weekly basis | PM-maintained log updated weekly | PM status update | PM | Weekly | Free text | Current week | Y | PMs self-report escalations / decisions needed per project / acct; Portfolio Office analyses each report, validates. | Acct delivery weekly reports (.PPT) |  |  | High |  | Delivery Health | PM per project |  | N/A | N/A | N/A | N/A | Syed | 2026-05-01
REL 3 | 40 | Cost RAG per project | Delivery Health | Project Status | Measures the project as a whole in terms of whether the forecast cost is in line with approved budget. (Budget RAG: Green = is in line with approved budget). | Red: project is over budget. Amber: project at risk of going over budget unless action is taken. Green = not over budget & not at risk of going over. | PM provides cost actuals vs approved budget at weekly account review | PM status update | PM | Weekly | RAG (G/A/R) | Current week | N |  |  | Actuals in Finance system; forecast held informally by PM. No single source. No automated consolidation. | Introduce standard project budget tracker (template). Finance to share actuals monthly. PM to update forecast. Portfolio Office to consolidate. | High |  | Delivery Health | PM per project | Red: project is over budget. Amber: project at risk of going over budget unless action is taken. Green = not over budget & not at risk of going over. | Not over budget & not at risk of going over. | At risk of going over budget unless action is taken. | Over budget | Green | Syed | 2026-05-01
REL 3 | 41 | Deals > 4 months in the pipeline | Commercial | Pipeline | Count of all on going deals (not yet been won) which have been in the pipeline for over 4 months | COUNT(Ongoing deals in the pipeline over 4 months) | CPs log deals in Zen X | Zen X | Client Partner | Weekly | Count + detail | Current week | N | Zn X not consistently used by all CPs. Pipeline values not reliably maintained. |  | Zen X hygiene is inconsistent. Pipeline value not a reliable source of truth. | Enforce Zen X pipeline hygiene standard. Weekly CP pipeline review. Portfolio Office extracts pipeline value each Friday. | Medium |  | Commercial | Client Partner |  | N/A | N/A | N/A | N/A | Mike
Note on AC36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Via email
Note on AC37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Via email
Note on AC38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Via email
Note on AC39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Via email

## Capability Summary
Capability Assessment Summary ¦ nxzen Portfolio Office ¦ DRAFT May 2026
# | Metric Name | Category | Capability (Y / N / Partial) | If YES — Current Process / Source | If NO — Gap & Process to Implement | Priority
1 | Active Projects | Portfolio Snapshot | Y (partial) | Finance have a list of all projects Extract from Dynamics | Would need to count only active projects (e.g. remove managed svcs, etc.) Filter extract to only counts active projects | High
2 | Active Clients | Portfolio Snapshot | Y (partial) | Finance have a list of all projects Extract from Dynamics shows customer (Client) | Would need to count only clients with a current active project(s) (e.g. remove managed svcs, etc.) Filter extract to only counts clients with an active project(s) | High
3 | Overall RAG Status | Portfolio Snapshot | Y (partial) | PMs self-report RAG per project / acct; Portfolio Office analyses each report, validates. No Portfolio / overall RAG Acct delivery weekly reports (.PPT) | Currently no overall / portfolio RAG status Need to apply portfolio / overall RAG criteria & apply for all active projects | High
4 | Overall RAG — Red % | Portfolio Snapshot | Y (partial) | PMs self-report RAG per project / acct; Portfolio Office analyses each report, validates. No Portfolio / overall RAG Acct delivery weekly reports (.PPT) | Currently no overall / portfolio RAG status Need to apply portfolio / overall RAG criteria & apply for all active projects | High
5 | Overall RAG — Amber % | Portfolio Snapshot | Y (partial) | PMs self-report RAG per project / acct; Portfolio Office analyses each report, validates. No Portfolio / overall RAG Acct delivery weekly reports (.PPT) | Currently no overall / portfolio RAG status Need to apply portfolio / overall RAG criteria & apply for all active projects | High
6 | Overall RAG — Green % | Portfolio Snapshot | Y (partial) | PMs self-report RAG per project / acct; Portfolio Office analyses each report, validates. No Portfolio / overall RAG Acct delivery weekly reports (.PPT) | Currently no overall / portfolio RAG status Need to apply portfolio / overall RAG criteria & apply for all active projects | High
7 | On Time % | Portfolio Snapshot | Y (partial) | PMs self-report milestones per project / acct; Portfolio Office analyses each report, validates. No Portfolio / overall % on time Acct delivery weekly reports (.PPT) | No standard milestone tracking tool or format across all PMs. Schedule data not consolidated. Define standard milestone template; PMs update weekly; Portfolio Office validates & consolidates at account review. Automate extraction via AI agent. | High
8 | Projects Behind Schedule (count) | Portfolio Snapshot | Y (partial) | PMs self-report milestones per project / acct; Portfolio Office analyses each report, validates. No Portfolio / overall behind schedule count Acct delivery weekly reports (.PPT) | No standard milestone tracking tool or format across all PMs. Schedule data not consolidated. Define standard milestone template; PMs update weekly; Portfolio Office validates & consolidates at account review. Automate extraction via AI agent. | High
9 | On Budget % | Portfolio Snapshot | N | Budget data held in Finance system but not linked to project register or dashboard. No standard budget tracker per project. | Actuals in Finance system; forecast held informally by PM. No single source. No automated consolidation. Introduce standard project budget tracker (template). Finance to share actuals monthly. PM to update forecast. Portfolio Office to consolidate. | High
10 | Projects Over Budget (count) | Portfolio Snapshot | N | Budget data held in Finance system but not linked to project register or dashboard. No standard budget tracker per project. | Actuals in Finance system; forecast held informally by PM. No single source. No automated consolidation. Introduce standard project budget tracker (template). Finance to share actuals monthly. PM to update forecast. Portfolio Office to consolidate. | High
11 | Resource Gaps Flagged | Portfolio Snapshot | Y (partial) | PMs flag resource gaps verbally in account reviews. Not formally tracked or logged. Verbal account review notes | Gaps flagged informally — no structured log or consistent criteria. Add resource gap field to weekly PM status template. Log in project register. Alert Portfolio Office when flagged. | Medium
12 | Client Satisfaction Score | Portfolio Snapshot | N | No formal client satisfaction process or survey tool in place. | CSAT not systematically collected. CPs have informal client sentiment but no structured data. Define lightweight CSAT process (1–5 rating + comment at milestone/monthly). CP collects and logs. Portfolio Office aggregates. | High
13 | Utilisation – UK (overall) | Resource & Utilisation | Y (partial) | Timesheets saved weekly. BI report can separate UK & IN users. Dynamics Timesheets | Currently report on current / past week & month not rolling 4 weeks Need to confirm the calculation with Saurabh Build automated utilisation calculation from timesheet data; surface weekly in dashboard. | Medium
14 | Utilisation – India (overall) | Resource & Utilisation | Y (partial) | Timesheets saved weekly. BI report can separate UK & IN users. Dynamics Timesheets | Currently report on current / past week & month not rolling 4 weeks Need to confirm the calculation with Saurabh Build automated utilisation calculation from timesheet data; surface weekly in dashboard. | High
15 | Utilisation – by Practice (Renewables & Eng) | Resource & Utilisation | N |  | No practice-level tagging in timesheet or resource data. Cannot slice utilisation by practice. Tag all resources with practice/sub-proposition in resource system. Build grouping logic in dashboard. | High
16 | Utilisation – by Practice (Data Intelligence & AI) | Resource & Utilisation | N |  | No practice-level tagging in timesheet or resource data. Cannot slice utilisation by practice. Tag all resources with practice/sub-proposition in resource system. Build grouping logic in dashboard. | High
17 | Utilisation – by Practice (Cyber Security) | Resource & Utilisation | N |  | No practice-level tagging in timesheet or resource data. Cannot slice utilisation by practice. Tag all resources with practice/sub-proposition in resource system. Build grouping logic in dashboard. | High
18 | Utilisation – by Practice (Apps & Development) | Resource & Utilisation | N |  | No practice-level tagging in timesheet or resource data. Cannot slice utilisation by practice. Tag all resources with practice/sub-proposition in resource system. Build grouping logic in dashboard. | High
19 | Utilisation – by Practice (OT) | Resource & Utilisation | N |  | No practice-level tagging in timesheet or resource data. Cannot slice utilisation by practice. Tag all resources with practice/sub-proposition in resource system. Build grouping logic in dashboard. | High
20 | Unassigned Resources % | Resource & Utilisation | Y | Users log time and select "Type" "unassigned" Dynamics Timesheets |  | High
21 | Unbillable Resources % | Resource & Utilisation | Y | Users log time against "Type" & "Project" Dynamics Timesheets |  | Medium
22 | Schedule RAG per Project | Delivery Health | Y (partial) |  | Each PM uses different tools (Excel, MS Project, Jira). No baseline plan consistently maintained. Mandate standard milestone plan template. PMs update weekly. RAG auto-calculated. Portfolio Office reviews in account review. | High
23 | Target Margin RAG per Project | Delivery Health | N |  | Actuals in Finance system; forecast held informally by PM. No single source. No automated consolidation. Introduce standard project budget tracker (template). Finance to share actuals monthly. PM to update forecast. Portfolio Office to consolidate. | High
24 | Resource RAG per Project | Delivery Health | Y (partial) | PMs informally assess resource health. Not formally documented or logged against criteria. Verbal PM update | No formal resource requirement plan per project to compare against. Define standard resource plan template per project. PM assesses weekly against criteria. Log in project register. | Medium
25 | Scope RAG per Project | Delivery Health | N | Change log and scope baseline not maintained consistently across projects. | No standard change log or scope baseline documentation per active project. Mandate scope baseline document and change log per active project. PM updates weekly. RAG assessed against criteria. | High
26 | Open Risks per Project | Delivery Health | Y (partial) | Risk logs exist informally per PM but no standard format and no consolidated view. | No standard risk register template or consolidated risk log. No consistent severity rating scale. Define standard risk register template with probability/impact scoring. PMs update weekly. Portfolio Office consolidates and surfaces High risks. | High
27 | Open Issues per Project | Delivery Health | Y (partial) | Issues not formally tracked. Raised verbally in account reviews but not logged. | No standard issue log. Issues not differentiated from risks. Define and mandate issue log (separate from risk log). PMs update weekly. Portfolio Office consolidates. | High
28 | Total Portfolio Value | Commercial | Y | Existing Finance process included in the Month End pack Zen X + Finance system |  | Medium
29 | Revenue Recognised MTD | Commercial | Y | Finance recognises revenue monthly per project. Data exists but not surfaced in dashboard. Finance accounting system & spreadsheets |  | Medium
30 | Revenue vs Plan Variance | Commercial | Y | Existing Finance process included in the Month End pack Finance accounting system & spreadsheets | Finance to produce monthly revenue plan at project level. Portfolio Office consolidates. Compare to actuals monthly. | High
31 | Average Project Margin % | Commercial | Y | Existing Finance process included in the Month End pack Finance accounting system & spreadsheets | Finance to produce per-project margin statement monthly. Portfolio Office aggregates. Dashboard shows average and per-project. | High
32 | Billable Utilisation % | Commercial | Y (partial) | Timesheets saved weekly. BI report can separate UK & IN users. Dynamics Timesheets |  | High
33 | Win Rate (6-month rolling) | Commercial | N | Win/loss data not consistently logged in Zen X. Tracked informally by CPs. | Pitches and outcomes not systematically recorded. No Zen X discipline enforced. Mandate CP updates Zen X at each stage: pitched, won, lost. Define 'pitched' (formal proposal submitted). Portfolio Office extracts monthly. | High
34 | Pipeline Value | Commercial | N | Zen X not consistently used by all CPs. Pipeline values not reliably maintained. | Zen X hygiene is inconsistent. Pipeline value not a reliable source of truth. Enforce Zen X pipeline hygiene standard. Weekly CP pipeline review. Portfolio Office extracts pipeline value each Friday. | High
35 | Repeat Business Rate % | Commercial | N | Repeat vs new business not formally categorised in Zen X or Finance. | No field in Zen X or project register to flag new vs repeat client engagement. Add New vs Repeat flag to project register and Zen X. CP confirms at kick-off. Finance validates. | Medium
36 | Average Days to Contract | Commercial | N | Contract dates not consistently logged in Zen X. Legal/procurement cycle not tracked. | No systematic tracking of bid-to-contract timeline. Log bid submission date and contract signed date in Zen X for all opportunities. Calculate automatically. | Medium
37 | Planned vs Actual Invoicing | Commercial | N |  | No invoice schedule is formally documented at project level. Invoicing is tracked in the Finance system but not compared against a planned schedule. No consolidated portfolio-level invoicing view exists. 1. Mandate CP/Finance to document an invoice schedule (date, milestone trigger, expected value) at active project kick-off. 2. Finance records actuals in the same tracker post-invoice. 3. Portfolio Office consolidates monthly. 4. Surface planned vs actual in dashboard with RAG: Green ≤±5%, Amber 6–15%, Red >15% or invoice missed entirely. | High
38 | Gross Margin £ (per project and portfolio) | Commercial | Y | Finance accounting system & spreadsheets |  | High
39 | Escalations and decisions required per project | Delivery Health | Y | PMs self-report escalations / decisions needed per project / acct; Portfolio Office analyses each report, validates. Acct delivery weekly reports (.PPT) |  | High
40 | Cost RAG per project | Delivery Health | N |  | Actuals in Finance system; forecast held informally by PM. No single source. No automated consolidation. Introduce standard project budget tracker (template). Finance to share actuals monthly. PM to update forecast. Portfolio Office to consolidate. | High
41 | Deals > 4 months in the pipeline | Commercial | N | Zn X not consistently used by all CPs. Pipeline values not reliably maintained. | Zen X hygiene is inconsistent. Pipeline value not a reliable source of truth. Enforce Zen X pipeline hygiene standard. Weekly CP pipeline review. Portfolio Office extracts pipeline value each Friday. | Medium
Y | 8 | 19.51%
N | 17 | 41.46%
Y (partial) | 16 | 39.02%
Total | 41
Check | 41

## Glossary & Guide
Glossary & Column Guide ¦ nxzen Portfolio Office Metric Catalogue
COLUMN DEFINITIONS
Metric Name | The name of the metric as it appears on the Portfolio Dashboard.
Category | Top-level grouping: Portfolio Snapshot ¦ Resource & Utilisation ¦ Delivery Health ¦ Commercial.
Sub-Category | Second-level grouping within the category.
Description | Plain-English explanation of what the metric measures and why it matters.
Calculation / Formula | Precise formula or calculation logic. References specific data fields.
Data Source (Process) | The business process or activity that generates the underlying data.
Source System / Tool | The technology, system, or file where the data lives or will live.
Data Owner | The role or team responsible for providing accurate data for this metric.
Update Frequency | How often the metric should be refreshed (Weekly / Monthly / On event).
Unit / Format | How the metric is expressed: count, %, £, days, RAG, etc.
Reporting Period | The time window the metric covers (e.g., current week, MTD, rolling 6 months).
Current Capability (Y/N) | Y = data and process exist to report today. Y (partial) = data exists but incomplete or manual. N = capability does not exist.
If YES — Current Process | For Y or Y (partial): description of how the metric is currently produced and by whom.
If YES — Data Source(s) | For Y or Y (partial): the specific file, system, or report used today.
If NO — Gap Description | For N or Y (partial): description of what is missing (data, process, system, discipline).
If NO — Process to Implement | For N or Y (partial): the steps required to establish the capability.
Priority to Implement | High = blocking dashboard launch. Medium = important but workaround exists. Low = nice-to-have.
Target Date | Target date for capability to be in place (where applicable).
Dashboard Section | Which section of the Portfolio Dashboard this metric appears in.
KPI Owner | The individual ultimately accountable for this metric being accurate and up to date.
Notes / Assumptions | Any caveats, exclusions, scope limitations, or context needed to interpret the metric correctly.
RAG Green / Amber / Red Threshold | The threshold values used to calculate the RAG status for this metric.
Benchmark / Target | The target or aspirational value for this metric, or a benchmark from the wireframe.
KEY TERMS
RAG Status | Red / Amber / Green health indicator. Criteria defined per metric and in the dashboard design document.
Managed Services | Excluded from portfolio scope for this dashboard. Tracked separately.
Portfolio Office | Laura Hargrave (owner). Responsible for consolidating data, maintaining this catalogue, and producing the weekly dashboard.
Account Review | Weekly structured conversation between PM/CP and Portfolio Office to capture project status data.
PM | Project Manager — responsible for day-to-day delivery data (schedule, risk, resource, budget).
CP | Client Partner — responsible for commercial and client relationship data.
nxzen UK | Scope of this dashboard. India resources included in utilisation metrics but India projects excluded unless delivered jointly.
Billable Utilisation | Hours charged to a client engagement / total contracted hours available. Excludes leave and internal time.
Pipeline | Opportunities tracked in CRM from Prospect stage through to Negotiation. Excludes Won/Lost/On Hold.
Revenue Recognised | Revenue formally recognised under the company's accounting policy. Not invoiced or received — recognised.

## Suggested Additions
Suggested Additional Metrics & Fields ¦ For Discussion
Metric / Field | Rationale / Why It Matters | Priority
Days Since Last Client Update | Flags projects where the CP has not logged a client interaction recently. Early warning of relationship drift. Helps Portfolio Office prompt CPs proactively. | High
Forecast Completion Date vs Baseline | For each project: original end date vs current forecast end date. Quantifies schedule drift more precisely than RAG alone. | High
Revenue at Risk (£) | Value of active project revenue at risk based on Red/Amber-rated projects. Aggregated commercial exposure view for leadership. | High
Gross Margin £ per Project | Absolute margin value (not just %) allows leadership to prioritise by commercial impact, not just percentage. | High
Open High Risks | Draw attention to any risks classed as High or Very High. | Medium
Staff Sentiment / Wellbeing Flag | Simple weekly pulse (Green/Amber/Red) per project team flagged by PM. Early indicator of delivery risk from people fatigue or conflict. | Medium
Quality RAG per Project | Measure how we performed at each project stage / gate (standards yet to be defined and agreed. Green = all gate criteria met, Amber = ≤2 minor fails v gate criteria, Red = 1 or more major fails or >2 minors v gate criteria) | Medium
Days in Current Phase | How long each project has been in its current phase (Discovery, Design, Build etc). Flags stalled projects before they become Red. | Medium
Change Requests Raised (count) | Number of formal change requests raised per project per period. Proxy for scope stability and client behaviour. | Medium
Invoice Outstanding > 30 Days (£) | Value of invoices unpaid beyond terms. Finance health indicator; also flags client relationship risk. | Medium
Contractor vs Permanent Split (%) | Proportion of delivery resource that is contractor vs permanent. Impacts margin and risk profile. | Medium
Skills Gap Index | For each project: number of required skills not covered by current allocation. More precise than Resource RAG. | Medium
Project Profitability at Completion (PAC) | Forecast final margin at project completion, updated monthly. Better forward indicator than margin-to-date. | High
NPS / Client Health Score | Structured Net Promoter Score or health score collected quarterly from key client stakeholders. More rigorous than ad-hoc CSAT. | Medium
Time to Mobilise (days) | Days from contract signed to project kick-off. Measures internal efficiency in standing up new projects. | Low
Portfolio Concentration Risk | % of total portfolio revenue from single largest client. Risk management metric for leadership. | Low
Lessons Learned Captured (Y/N) | Flag per completed project whether a lessons learned exercise was conducted and documented. Drives continuous improvement. | Low

## Lists
MVP
REL 1
REL 2
REL 3
TBC

## Deleted Metrics
nxzen Portfolio Office ¦ Metric Definition Catalogue ¦ DRAFT — April 2026
| METRIC IDENTITY |  |  |  | DEFINITION |  |  | DATA & GOVERNANCE |  |  |  |  | CAPABILITY ASSESSMENT | [6 empty] | DASHBOARD |  |  | THRESHOLDS
Release | # | Metric Name | Category | Sub-Category | Description | Calculation / Formula | Data Source (Process) | Source System / Tool | Data Owner | Update Frequency | Unit / Format | Reporting Period | Current Capability (Y / N) | If YES — Current Process | If YES — Data Source(s) | If NO — Gap Description | If NO — Process to Implement | Priority to Implement | Target Date | Dashboard Section | KPI / Measure Owner | Notes / Assumptions | RAG Green Threshold | RAG Amber Threshold | RAG Red Threshold | Benchmark / Target | Validated By | Date | Comments / Q's
| 11 | Open High Risks (count) | Portfolio Snapshot | Delivery Indicators | Count of open high or very high risks across all active projects. | COUNT (Risk Status = Open & high or very high) | PM-maintained risk log updated at weekly account review | Risk log (Excel / PPM) | PM (owner), Portfolio Office (consolidated) | Weekly | Count (#) | Current week | N | Risk logs exist informally per PM but no standard format and no consolidated view. |  | No standard risk register template or consolidated risk log. No consistent severity rating scale. | Define standard risk register template with probability/impact scoring. PMs update weekly. Portfolio Office consolidates and surfaces High risks. | High | 01/06/2026 | Portfolio Snapshot / Delivery Health | PM per project | See nxzen group risk register for thresholds / ratings. | 0 | 1–2 | ≥2 | 0 | Syed | 2026-05-01
| 35 | Budget Variance % per Project | Commercial | Budget | Variance between forecast total cost and approved budget for each active project. | (Forecast Cost − Approved Budget) / Approved Budget × 100. | PM provides cost forecast; Finance provides actuals | Finance system + PM budget tracker | Finance (actuals), PM (forecast) | Monthly | % (one decimal) | Current month forecast vs baseline | N | Budget data held in Finance system but not linked to project register or dashboard. No standard budget tracker per project. |  | Actuals in Finance system; forecast held informally by PM. No single source. No automated consolidation. | Introduce standard project budget tracker (template). Finance to share actuals monthly. PM to update forecast. Portfolio Office to consolidate. | High | 01/06/2026 | Commercial | Finance | Displayed as bar chart in dashboard. Green ±5%, Amber >5–15%, Red >15%. | ±5% | >5–15% | >15% | ±5% | Sarah B | N/A | Reviewed with Sarah B on 29/04/26. Data required for this measure is already available in report 21 Target Margin RAG per project.
| 37 | Planned Budget vs Actual Cost | Commercial | Budget | Comparison of approved active project budget against actual costs incurred to date (and forecast to completion). Measures cost control and financial health at project and portfolio level. Distinct from Budget RAG (#20) which is a directional indicator — this metric provides the underlying £ figures. | At project level: Actual Cost to Date vs Budget to Date (earned value approach where possible). Variance = Actual Cost − Budget. Variance % = (Actual Cost − Budget) / Budget × 100. Also report: Estimate at Completion (EAC) vs Total Approved Budget to give a completion forecast. Portfolio total = SUM across all active projects. | Finance system provides actual costs (timesheets converted to cost + direct expenses). PM provides budget baseline and cost forecast to completion. Finance validates. | Finance / Accounting system (actuals: labour cost + expenses) + Project budget tracker (baseline + forecast) | Finance (actuals), PM (budget baseline and forecast to completion) | Monthly (minimum); weekly where Finance system allows | £ (GBP) — Actual Cost, Budget to Date, Variance £, Variance %, EAC vs Total Budget | Current month actuals; cumulative to date; forecast to completion | N |  |  | Actual costs are held in the Finance system but are not systematically compared against a project-level budget baseline. No standard budget tracker exists per project. Forecast to completion (EAC) is not formally produced. Cost data is not currently surfaced at portfolio level. | 1. Define standard project budget template: approved budget by phase/month, actual cost feed from Finance, PM-updated forecast to completion. 2. Finance to provide monthly actual cost report per project code. 3. PM to update forecast to completion monthly. 4. Portfolio Office consolidates and calculates variance. 5. RAG-rate: Green ±5%, Amber >5–15%, Red >15%. 6. Flag projects where EAC exceeds total approved budget. | High | 01/06/2026 | Commercial | Finance | Labour cost = hours logged × blended day rate (or agreed internal cost rate). Expenses = receipted project expenses. Excludes indirect overhead allocation unless agreed with Finance. Budget baseline is the approved budget at active project kick-off (or last approved change order if scope change has been agreed). Do not use forecast as baseline — the baseline must be locked. | Actual cost within ±5% of budget to date | Actual cost >5–15% over budget to date, or EAC >5–15% over total budget | Actual cost >15% over budget to date, or EAC >15% over total budget, or forecast to completion exceeds approved budget | Actual cost = Budget to date (0% variance) | Sarah B | N/A | Reviewed with Sarah B on 29/04/26. Data required for this measure is already available in report 21 Target Margin RAG per project.