## Cover
Version | Status | Date | Author | Comments
v1 | Old | 2026-04-17 | Laura Hargrave | First draft for comment
v2 | Old | 2026-04-29 | Alf Pendlebury | Added data owner & data source to relevant tabs
v3 | Old | 2026-04-29 | Laura Hargrave | Added Governance Checkpoints tab & associated info
v4 | Current | 2026-05-08 | Alf Pendlebury | Added Roles & Responsibilities tab & asscociated info. Finalised latest data updates to project tabs. Proj data now accurate as at 08/05/26.
Notes:
N1:

## 📋 Instructions
PURPOSE
This register is the single source of truth for all active nxzen UK project data. It is completed weekly by Project Managers and Client Partners, then processed by the Portfolio Office to generate the Friday Portfolio Review dashboard.
WHO COMPLETES WHAT
Project Managers | Complete the '🗂 Project Register', '🚦 Weekly Status Update', and '⚠️ Risks & Issues' tabs for each of your projects.
Client Partners | Complete the '💼 Commercial' tab for each of your accounts.
Resource Manager | Complete the '👥 Resource & Utilisation' tab each week.
Finance | Complete the '🗂 Project Register' columns XXX
Portfolio Office | Validate all inputs, track governance checkpoints in '✅ Gov Checkpoints' tab, run the report / automation, and distribute the dashboard by Friday PM.
WEEKLY RHYTHM
Thursday EOD | PMs complete the '🗂 Project Register', '🚦 Weekly Status Update', and '⚠️ Risks & Issues' tabs for project ahead of their respecitve weekly elivery review call (Mon- Thurs).
Friday AM | Portfolio Office runs AI (Claude) automation and generates dashboard.
Friday PM | Dashboard distributed to Mohamed Syedian ahead of Tuesday SLT. PO saves a copy end of week for reference
IMPORTANT RULES
1. Do NOT change column headers or tab names. | The automation reads specific cell locations. Changing structure will break the dashboard.
2. Use the dropdowns provided. | RAG status, Phase, Practice, and other fields have validated dropdowns. Do not type freehand.
3. Every active project must have a row. | If a project is new, add a row in the Project Register first before updating status.
4. Never delete rows — mark as Closed instead. | Set Status = 'Closed' in the Project Register to remove from active dashboard view.
5. Red RAG must have a comment. | Any Red rating in the Weekly Status Update requires a comment in the 'Key Flag / Comment' column.
6. RAG Criteria | xxx

## Roles & Responsibilities
Project Register Tab
Responsible to populate | Ref | Project Name | Client | Sub-Prop / Practice | Current Phase | Status | Start Date | End Date (Baseline) | End Date (Forecast) | Days Slippage | Contract Value (£) | Margin Target (%) | PM Name | CP Name | Project Code | Notes
Portfolio Office | TRUE | TRUE | TRUE | TRUE |  |  | TRUE | TRUE |  |  |  |  | TRUE
Project Manager |  |  |  |  | TRUE | TRUE |  |  | TRUE | TRUE |  |  |  |  | TRUE | TRUE
Client Parter | [10 empty] | TRUE | TRUE |  | TRUE
Finance
Resource Manager
Weekly Status Update Tab
Responsible to populate | Ref | Project Name | Client | Week Ending | Schedule RAG | Resource RAG | Scope RAG | Budget RAG | Overall RAG | Key Flag / Comment | Next Milestone | Milestone Due | Milestone Status | PM Name | Last Updated
Portfolio Office | TRUE | TRUE | TRUE | [10 empty] | TRUE
Project Manager |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE
Client Parter
Finance
Resource Manager
Risks and Issues Tab
Responsible to populate | Ref | Project Name | Client | Phase | Type | Rating | Description | Impact if Unmitigated | Mitigation / Action | Owner | Status | Date Raised
Portfolio Office | TRUE | TRUE | TRUE
Project Manager |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Client Parter
Finance
Resource Manager
Commercial Register Tab
Responsible to populate | Ref | Project Name | Client | CP Name | Contract Value (£) | Revenue Plan MTD (£) | Revenue Actual MTD (£) | Margin Forecast (%) | Opportunity Name | Pipeline Stage | Pipeline Value (£) | Repeat / New
Portfolio Office | TRUE | TRUE | TRUE
Project Manager
Client Parter |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Finance
Resource Manager
Resource and Utilisation Tab
Responsible to populate | Ref | Name | Practice | Region | Contract Hours/Wk | Leave Hours | Billable Hours | Non-Billable Hours | Utilisation % | Assigned Project(s) | Assignment Status | Notes
Portfolio Office | TRUE
Project Manager
Client Parter
Finance
Resource Manager |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Client Satisfaction Tab
Responsible to populate | Ref | Project Name | Client | Date Collected | Score (1-5) | Client Comment | Collected By | Next Collection Due
Portfolio Office | TRUE | TRUE | TRUE
Project Manager
Client Parter |  |  |  | TRUE | TRUE | TRUE | TRUE | TRUE
Finance
Resource Manager

## ✅ Gov Checkpoints
✅ Gov Checkpoints ¦ Portfolio Office — Central Source of Truth ¦ Portfolio tracks evidence; delivery teams run the meetings
GOVERNANCE CHECKPOINTS ¦ Lifecycle: Bid/Proposal > Initiate > Plan > Delivery > Close ¦ Delivery flow within Delivery phase: Design > Build > Test > Deploy
Portfolio Office | Portfolio Office | Portfolio Office | Portfolio Office | Portfolio Office | Portfolio Office | PM | PM | PM | PM | PM | PM | Portfolio Office
Portfolio Office | Portfolio Office | Portfolio Office | Portfolio Office | Portfolio Office | Portfolio Office | n/a Update Here | n/a Update Here | n/a Update Here | n/a Update Here | n/a Update Here | n/a Update Here | n/a Update Here
Ref | Phase | Checkpoint | Owner | What it covers | Evidence — how Portfolio Office tracks it | P001 CRM Modernisation UKPN ¦ UAT | P002 ERP Integration UKPN ¦ Build | P003 Data Platform SSE ¦ Discovery | P004 Digital Strategy ENW ¦ Discovery | P005 Cyber Maturity Nat. Grid ¦ Build | P006 OT Security SP Energy ¦ Discovery | Notes / Evidence Detail
B1 | Bid/Proposal | Bid / No-bid review | Portfolio Office | Portfolio Office confirms commercial viability, resource availability, margin expectations and strategic fit before committing to a bid. Hard gate — no bid submitted without Portfolio Office sign-off. | Decision (Proceed / No-bid) recorded with rationale and Client Partner sign-off. Date and decision logged in register. Stored against project ref. | Complete | Complete | Complete | Complete | Complete | Complete
B2 | Bid/Proposal | Technical solutioning sign-off | Joint | Delivery team presents proposed technical approach, stack, architecture and effort estimates. Portfolio confirms resource and timeline are realistic before submission. | Solution summary doc or sign-off email filed. Date, attendees and any conditions recorded in Notes column. Portfolio records outcome — does not chair meeting. | Complete | Complete | Complete | Complete | Complete | Complete
B3 | Bid/Proposal | Risk & assumptions register opened | Joint | Delivery raises key delivery risks and commercial assumptions in the bid. Portfolio validates completeness and realism before submission to client. | Risk log version number and review date recorded. PM confirmation noted. Linked to Risks & Issues tab on award. | Complete | Complete | Complete | Complete | Complete | Complete
I1 | Initiate | Project kick-off gate | Portfolio Office | Hard gate before any delivery work begins. Signed contract confirmed, project code issued, PM named, baseline scope and budget agreed. No work starts without this. | Contract reference, project code, PM name and gate date recorded. Gate status = Pass / Conditional / Fail. Logged in Project Register. | Complete | Complete | Complete | Complete | Complete | In Progress
I2 | Initiate | Project charter approved | Joint | Objectives, success criteria, constraints, exclusions, governance contacts and escalation path documented and agreed with client. | Charter document version and client sign-off date recorded. Portfolio holds the approved charter. Any conditions noted. | Complete | Complete | Complete | Complete | Complete | In Progress
I3 | Initiate | Stakeholder & RACI confirmed | Portfolio Office | Client-side contacts, internal nxzen team, escalation path and communication cadence agreed and documented. | Named contacts and RACI version logged. Portfolio records confirmation date. Escalation path tested (email/call confirmed with client sponsor). | Complete | Complete | Complete | Complete | Complete | In Progress
I4 | Initiate | Technical architecture review | Delivery Team | Delivery team presents proposed architecture to internal technical lead or CTO. Solution reviewed for quality, nxzen standards, risk and client constraints. | Portfolio records: reviewed (Y/N), reviewer name, date, any conditions raised. Delivery team owns and runs the review. Portfolio logs outcome only. | Complete | Complete | Complete | Complete | Complete | In Progress
P1 | Plan | Baseline plan approved | Portfolio Office | Project schedule, milestones, dependencies and critical path baselined and approved. Portfolio holds the approved baseline for all future change tracking. | Baseline plan version saved with approval date and PM sign-off. Any variances from bid assumptions noted. Baseline locked in register. | Complete | Complete | In Progress | In Progress | Complete | Not Started
P2 | Plan | Design review sign-off | Delivery Team | UX, architecture or data design reviewed and approved before build begins. Covers functional design, non-functional requirements and integration points. Entry gate to Build — no build starts without this. | Portfolio records: sign-off received (Y/N), reviewer name, date, and whether any CRs were raised as a result. Delivery team runs the review. | Complete | Complete | In Progress | In Progress | Complete | Not Started
P3 | Plan | Resource confirmed | Joint | Named individuals assigned to the project before delivery starts. Skill gaps identified. Interim or contractor resource plan agreed if gaps exist. | Named resource list logged against project ref. Any gaps or contractor requirements flagged to Resource Manager. Confirmation date recorded. Linked to Resource tab. | Complete | Complete | In Progress | In Progress | Complete | Not Started
P4 | Plan | Quality & test strategy agreed | Delivery Team | Test approach, environments, test types (SIT, UAT, regression), entry/exit criteria and client acceptance process defined and agreed before build begins. | Test strategy document on file. Portfolio records: agreed (Y/N), date, UAT lead named (client and internal). Delivery team owns the document. | Complete | Complete | In Progress | In Progress | Complete | Not Started
D1 | Delivery | Design sign-off (entry to Build) | Delivery Team | Functional and technical design formally signed off by client and internal lead before any build activity begins. Covers UI/UX, data model, integrations and non-functional requirements. | Portfolio records: signed off (Y/N), client contact, internal reviewer, date. Any open design items that are conditional to build noted. Delivery team runs the review; Portfolio logs outcome. | In Progress | In Progress | Not Started | Not Started | In Progress | Not Started
D2 | Delivery | Build checkpoint (sprint / phase review) | Delivery Team | Delivery team runs regular sprint reviews or phase checkpoints. Progress against plan, quality, velocity and blockers reviewed at each checkpoint. | Portfolio tracks via 🚦 Weekly Status tab: RAG per week, velocity trend, blockers escalated. Portfolio does not attend sprint ceremonies. Flags to SLT if Overall RAG = Red for 2+ consecutive weeks. | In Progress | In Progress | Not Started | Not Started | In Progress | Not Started
D3 | Delivery | Change control checkpoint | Portfolio Office | All changes to scope, budget or timeline logged by PM and commercially approved by Client Partner before implementation. Portfolio holds the consolidated CR log. | CR log maintained in register. Each CR must have: raised date, description, £ value impact, approval status, and approved date. Portfolio tracks cumulative impact on baseline budget and schedule. | In Progress | In Progress | Not Started | Not Started | In Progress | Not Started
D4 | Delivery | Test entry sign-off (SIT / UAT entry) | Delivery Team | Defined entry criteria for System Integration Testing or UAT must be met and confirmed before testing begins. Delivery team confirms readiness formally. | Portfolio records: entry criteria met (Y/N), test start date, any conditions accepted. Evidence = test readiness report or PM sign-off email. Delivery team owns the gate. | In Progress | In Progress | Not Started | Not Started | In Progress | Not Started
D5 | Delivery | UAT exit / client acceptance | Joint | Client formally accepts UAT results and signs off on the build before go-live. This is the primary commercial acceptance milestone and triggers final invoicing. | Portfolio records: sign-off received (Y/N), client contact name, date, outstanding defects agreed (if any). Updates forecast-to-complete and flags invoicing milestone to Commercial tab. | In Progress | In Progress | Not Started | Not Started | In Progress | Not Started
D6 | Delivery | Deploy readiness review (Go / No-go) | Delivery Team | Formal go/no-go decision against a defined deployment checklist covering: technical readiness, data migration, rollback plan, support arrangements and client comms. | Portfolio records: Go/No-go decision, decision maker, date, confirmed deployment window. Any No-go conditions and resolution plan noted. Delivery team chairs; Portfolio logs outcome. | In Progress | In Progress | Not Started | Not Started | In Progress | Not Started
C1 | Close | Deployment / go-live sign-off | Joint | Production release confirmed. Client acknowledges live status. Hypercare period and support arrangements agreed and communicated. | Portfolio updates project status to Closing. Deployment date, client confirming contact and hypercare start/end dates recorded. Commercial tab updated for final invoice trigger. | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
C2 | Close | Hypercare / stabilisation gate | Portfolio Office | Defined support period monitored post go-live. Issues tracked. Exit criteria for hypercare met before formal transition to client or BAU. | Portfolio tracks open issues during hypercare. Gate exit = all P1/P2 issues resolved, client sign-off on stability. Date of hypercare exit recorded. Status updated to Closing. | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
C3 | Close | Lessons learned | Delivery Team | Delivery team runs a structured retrospective covering what went well, what could improve, and actions for future projects. | Portfolio captures key themes across portfolio (not per-project detail). Delivery team owns and runs the session. Portfolio records: held (Y/N), date, top 3 themes noted. | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
C4 | Close | Project closure approved | Portfolio Office | Final sign-off that the project is complete. Covers: final financials reconciled, outcomes vs plan documented, client satisfaction score collected, resource released, project code closed in systems. | Closure checklist completed. Final margin vs target recorded in Commercial tab. Client satisfaction score logged in ⭐ Client Satisfaction tab. Project status set to Closed in Project Register. | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
Owner key: Portfolio Office = holds the gate, records evidence and escalates ¦ Delivery Team = runs the meeting and produces the artefact ¦ Joint = both must attend for the decision to be valid

## 🗂 Project Register
🗂 Project Register ¦ All Active nxzen UK Projects ¦ Updated: see cell P2
PROJECT IDENTITY |  |  | DATES & PHASE |  |  |  |  | COMMERCIAL |  |  | OWNERSHIP |  |  | STATUS
Portfolio Office | Portfolio Office | Portfolio Office | Portfolio Office | PM | PM | Portfolio Office | Portfolio Office | PM | PM | CP | CP | Portfolio Office | CP | PM | PM
MS Dynamic Project Operations | MS Dynamic Project Operations | MS Dynamic Project Operations | MS Dynamic Project Operations | n/a Update Here | n/a Update Here | MS Dynamic Project Operations | MS Dynamic Project Operations | n/a Update Here | n/a Update Here | ZenX | ZenX | MS Dynamic Project Operations | ZenX | n/a Update Here | n/a Update Here
Ref | Project Name | Client | Sub-Proposition / Practice | Current Phase | Status | Start Date | End Date (Baseline) | End Date (Forecast) | Days Slippage | Contract Value (£) | Margin Target (%) | PM Name | CP Name | Project Code | Notes
GB01_P001074 | Project - UKPN - Cyber Resilience Roles T&M | UK Power Networks (Operations) Ltd | Renewables & Engineering |  | Active | 2025-07-01 | 2026-12-31 |  |  |  |  | Amit Fadnavis | Sudhakar Nalla
GB01_P001021 | Project - UKPN - Income Management Mavis Faster Staging | UK Power Networks (Operations) Ltd | Renewables & Engineering |  | Active | 2026-01-05 | 2026-04-10 | 2026-12-15 |  |  |  | Danie Selvaraju | Sudhakar Nalla
GB01_P001073 | Project - UKPN - Nexus IMIB | UK Power Networks (Operations) Ltd | Renewables & Engineering | UAT | Active | 2026-02-01 | 2026-08-31 |  |  |  |  | MohamedMurshid S | Sudhakar Nalla
| UKPN - Distance to Fault & CAS Pole Pilot | UK Power Networks (Operations) Ltd | Renewables & Engineering |  | Active | 2026-03-01 | 2026-12-31 |  |  |  |  | Vasupradha | Sudhakar Nalla |  | New project
GB01_P001005 | Project - Eirgrid - Eirgrid PSSE to Power Factory | EirGrid plc | Renewables & Engineering |  | On Hold | 2025-08-01 | 2028-06-30 |  |  |  |  | Rodrigo Merino | Rodrigo Merino |  | The project has been placed on hold and may potentially be terminated.
GB01_P001006 | Project - Eirgrid - Eirgird Product Specialist T&M | EirGrid plc | Renewables & Engineering |  | Active | 2025-10-01 | 2026-04-30 |  |  |  |  | Rodrigo Merino | Rodrigo Merino |  | The project may be extended by a further three months - In discussion
GB01_P001010 | Project - ENWL - SAP Projects | Electricity North West Limited | Renewables & Engineering |  | Active | 2025-04-01 | 2027-03-31 |  |  |  |  | TamoghnaMihirDas gupta | David Butcher
| ENWL - Project Manager - IT Resilience SMR - TnM | Electricity North West Limited | Renewables & Engineering |  | Active | 2026-05-01 | 2026-10-30 |  |  |  |  | TamoghnaMihirDas gupta | David Butcher |  | New project
| WWU - Deed Digitalisation | Wales & West Utilities | Renewables & Engineering |  | Active | 2026-04-01 | 2027-01-31 |  |  |  |  | TamoghnaMihirDas gupta | Martin Ridley |  | New project
| WWU - Service Suite Upgrade & MFT | Wales & West Utilities | Renewables & Engineering | Design | Active | 2026-04-01 | 2026-12-31 |  |  |  |  | TamoghnaMihirDas gupta | Martin Ridley |  | New project
GB01_P001075 | Project - WWU - Open Text | Wales & West Utilities | Renewables & Engineering | Design | Active | 2026-03-08 09:00 | 2027-01-31 |  |  |  |  | TamoghnaMihirDas gupta | Martin Ridley
GB01_P001028 | Project - WWU- SAP Simplification Item - S/4 | Wales & West Utilities | Renewables & Engineering |  | Active | 2025-01-08 | 2026-11-30 |  |  |  |  | TamoghnaMihirDas gupta | Martin Ridley
GB01_P001026 | Project - WWU - S4 Resource and S4 Project Support New - FY26 | Wales & West Utilities | Renewables & Engineering |  | Active | 2025-04-01 | 2026-12-31 |  |  |  |  | TamoghnaMihirDas gupta | Martin Ridley
GB01_P001070 | Project - SGN - Dev Test FPP | Scotia Gas Networks Limited | Renewables & Engineering |  | Active | 2026-04-01 | 2027-03-31 |  |  |  |  | Anoop Prabhu | Alex Pitcher |  | Project consists of 5 FP SOW's
GB01_P001069 | Project - SGN - Dev Test T&M | Scotia Gas Networks Limited | Renewables & Engineering |  | Active | 2026-04-01 | 2027-03-31 |  |  |  |  | Anoop Prabhu | Alex Pitcher |  | Project consists of T&M SOW's

## 🚦 Weekly Status Update
🚦 Weekly Status Update ¦ Complete by Wednesday EOD ¦ PM-owned
PROJECT ID |  |  |  | RAG STATUS - REFER TO CRITERIA IN INSTRUCTIONS (this week) |  |  |  |  | KEY FLAG / COMMENT | MILESTONE |  |  | GOVERNANCE
Portfolio Office | Portfolio Office | 17.22 | PM | PM | PM | PM | PM | PM | PM | PM | PM | PM | Portfolio Office | PM
MS Dynamic Project Operations | MS Dynamic Project Operations | MS Dynamic Project Operations | n/a Update Here | n/a Update Here | n/a Update Here | n/a Update Here | n/a Update Here | n/a Update Here | n/a Update Here | n/a Update Here | n/a Update Here | n/a Update Here | MS Dynamic Project Ops | n/a Update Here
Ref | Project Name | Client | Week Ending | Schedule RAG | Resource RAG | Scope RAG | Budget RAG | Overall RAG | Key Flag / Comment (mandatory if any Red) | Next Milestone | Milestone Due | Milestone Status | PM Name | Last Updated
GB01_P001074 | Project - UKPN - Cyber Resilience Roles T&M | UK Power Networks (Operations) Ltd | 2026-05-08 | Green | Green | Green | Green | Green | 05/05: End of May PO to be confirmed. At Risk but client assured | PO confirmation | 2026-05-31 | At Risk | Amit Fadnavis | 2026-05-05
GB01_P001021 | Project - UKPN - Income Management Mavis Faster Staging | UK Power Networks (Operations) Ltd | 2026-05-08 | Green | Green | Green | Green | Green | 28/04: Project continued until Dec’26 |  |  | On Track | Danie Selvaraju | 2026-04-28
GB01_P001073 | Project - UKPN - Nexus IMIB | UK Power Networks (Operations) Ltd | 2026-05-08 | Amber | Green | Green | Green | Amber | 28/04: Very tight timelines. UAT started 27/04 and client resourcing not sufficient to meet deadlines, so we have needed to add in more resource to complete. | UAT Complete |  | At Risk | MohamedMurshid S | 2026-04-28
0 | UKPN - Distance to Fault & CAS Pole Pilot | UK Power Networks (Operations) Ltd | 2026-05-08 | Green | Green | Green | Green | Green | 05/05: Reduce timelines for pilot delivery. | Workshop | 2026-05-13 | On Track | Vasupradha | 2026-05-05
GB01_P001005 | Project - Eirgrid - Eirgrid PSSE to Power Factory | EirGrid plc | 2026-05-08 | Red | Green | Red | Green | Red | 05/05: Scheduling call with Procurement. £50k at risk. | Confirm proj statius |  | At Risk | Rodrigo Merino | 2026-05-05
GB01_P001006 | Project - Eirgrid - Eirgird Product Specialist T&M | EirGrid plc | 2026-05-08 | Green | Green | Green | Green | Green | 27/04: Currently discussing 3-month extension from under mid-May current PO |  |  |  | Rodrigo Merino | 2026-04-27
GB01_P001010 | Project - ENWL - SAP Projects | Electricity North West Limited | 2026-05-08 | Green | Green | Green | Green | Green | 06/05: CR status is green. Extension of 1 week accepted by client. ​ Separately the stabilization is in progress and on track against plan. | Complete Stabilisation plan |  | On Track | TamoghnaMihirDas gupta | 2026-05-06
0 | ENWL - Project Manager - IT Resilience SMR - TnM | Electricity North West Limited | 2026-05-08 | Green | Green | Green | Green | Green | 29/04: Srinivasan Neelakantan has been onboarded and working from SP ENW Location from 20th April. |  |  |  | TamoghnaMihirDas gupta | 2026-04-29
0 | WWU - Deed Digitalisation | Wales & West Utilities | 2026-05-08 | Green | Green | Green | Green | Green | 06/05: Client feedback to be incorporated into design and to be played back 07/05 during the Architecture Review Board (ARB) | Design review at ARB | 2026-05-07 | On Track | TamoghnaMihirDas gupta | 2026-05-06
0 | WWU - Service Suite Upgrade & MFT | Wales & West Utilities | 2026-05-08 | Green | Green | Green | Green | Green | 06/05: Received additional scope from client and working on impact assessment currently, to be shared next week. Project still in design phase. | Agree scope |  | On Track | TamoghnaMihirDas gupta | 2026-05-06
GB01_P001075 | Project - WWU - Open Text | Wales & West Utilities | 2026-05-08 | Amber | Amber | Amber | Amber | Amber | 06/05: New plan is being baselined and CR being agreed with the client. Once plan baselined and CR agreed, we can anticipate move back to green. | Meet with WWU Team |  | On Track | TamoghnaMihirDas gupta | 2026-05-06
GB01_P001028 | Project - WWU- SAP Simplification Item - S/4 | Wales & West Utilities | 2026-05-08 | Green | Green | Green | Green | Green |  | Submit work order |  |  | TamoghnaMihirDas gupta | 2026-04-29
GB01_P001026 | Project - WWU - S4 Resource and S4 Project Support New - FY26 | Wales & West Utilities | 2026-05-08 | Green | Green | Green | Green | Green | NGM DBP Decom – delivered and handover in progress | Complete handover |  |  | TamoghnaMihirDas gupta | 2026-04-29
GB01_P001070 | Project - SGN - Dev Test FPP | Scotia Gas Networks Limited | 2026-05-08 | Red | Green | Green | Red | Red | 07/05: Alex (CP) and project sponsor from SNG have aligned. SGN has not confirmed the testing start date. (Sudha). Need to re-baseline plan and commercials etc. Alex is on top of this issue. Trend is the same as previous week. | 07/05: IBM team onboarded today, kick off complete. (Praveen) | 2026-04-27 | Complete | Anoop Prabhu | 2026-05-07
GB01_P001069 | Project - SGN - Dev Test T&M | Scotia Gas Networks Limited | 2026-05-08 | Green | Green | Green | Green | Green | 07/05: Tracking green, no issues. |  |  |  | Anoop Prabhu | 2026-05-07

## ⚠️ Risks & Issues
⚠️ Risks & Issues Register ¦ PM-owned ¦ Updated Weekly
PROJECT |  |  |  | RISK / ISSUE DETAIL |  |  |  | MANAGEMENT
Portfolio Office | Portfolio Office | Portfolio Office | PM | PM | PM | PM | PM | PM | PM | PM | PM
MS Dynamic Proj Ops | MS Dynamic Proj Ops | MS Dynamic Proj Ops | Current Proj Status Excel | RAID | RAID | RAID | RAID | RAID | RAID | RAID | RAID
Ref | Project Name | Client | Phase | Type | Rating | Description | Impact if Unmitigated | Mitigation / Action | Owner | Status | Date Raised
GB01_P001074 | Project - UKPN - Cyber Resilience Roles T&M | UK Power Networks (Operations) Ltd | 0
GB01_P001021 | Project - UKPN - Income Management Mavis Faster Staging | UK Power Networks (Operations) Ltd | 0
GB01_P001073 | Project - UKPN - Nexus IMIB | UK Power Networks (Operations) Ltd | UAT
0 | UKPN - Distance to Fault & CAS Pole Pilot | UK Power Networks (Operations) Ltd | 0
GB01_P001005 | Project - Eirgrid - Eirgrid PSSE to Power Factory | EirGrid plc | 0 | Risk | High | Risk of non-payment as client not satisfied by work completed |  | CP scheduling meeting with Procurement to review and discuss next steps | R Merino | In Progress | 2026-05-01
GB01_P001006 | Project - Eirgrid - Eirgird Product Specialist T&M | EirGrid plc | 0
GB01_P001010 | Project - ENWL - SAP Projects | Electricity North West Limited | 0 | Risk | Medium | SAP BASIS and security – team composition is currently lacking skills |  | nxzen currently building in house team for SAP BASIS and security across all account. 06/05: No further update. | Tamo / Solman | In Progress | 2026-04-29
0 | ENWL - Project Manager - IT Resilience SMR - TnM | Electricity North West Limited | 0
0 | WWU - Deed Digitalisation | Wales & West Utilities | 0 | Risk | Medium | DEED Digitilisation solution – feedback on fitting client requirements |  | 06/05: Feedback received but probability reduced. | Nirmal Paul + Akhil Gupta | In Progress | 2026-04-29
0 | WWU - Service Suite Upgrade & MFT | Wales & West Utilities | Design | Risk | High | Secure MFT - Azure infrastructure Environment readiness / preparation is getting delayed. |  | 06/05: Risk of further slippage beyond the change request. | Tamo | In Progress | 2025-11-21
GB01_P001028 | Project - WWU- SAP Simplification Item - S/4 | Wales & West Utilities | 0 | Risk | Medium | Risk on Version Compatibilities mismatch |  | 06/05: clarification received | Venoje | Closed | 2026-04-29
GB01_P001026 | Project - WWU - S4 Resource and S4 Project Support New - FY26 | Wales & West Utilities | 0 | Risk | Medium | Risk of Delay in HLD Approval will have impact in Start of Development Activities | Note: Not clear which piece of work the risk is related to so have selected GB01_P001026 | 06/05: Still open, probability reduced | Venoje | In Progress | 2026-04-29
GB01_P0001026 | Project - WWU - S4 Resource and S4 Project Support New - FY26 | Wales & West Utilities | 0 | Risk | Medium | No agreement on the Level of completion of LLD to commence development activities | Note: Not clear which piece of work the risk is related to so have selected GB01_P001026 | 06/05: Still open, probability reduced | Venoje | In Progress | 2026-04-29
GB01_P001070 | Project - SGN - Dev Test FPP | Scotia Gas Networks Limited | 0 | Risk | Medium | Risk on IBM Infra being not supportive on Application support |  | 07/05: Anoop to escalate it with SGN. In progress | Anoop | In Progress | 2026-05-07
GB01_P001069 | Project - SGN - Dev Test T&M | Scotia Gas Networks Limited | 0 | Risk | Medium | We may lose business to competitors for Gas Control related work due to lack of skilled resources in the team |  | 07/05: Trying to support new resource starting next week, 2 days per week. June full time. Alex to confirm. If not available, revert to contractor. | Vikas | In Progress | 2026-05-07

## 💼 Commercial
💼 Commercial Register ¦ CP-owned ¦ Updated Monthly
PROJECT |  |  |  | REVENUE & MARGIN |  |  |  | PIPELINE
Portfolio Office | Portfolio Office | Portfolio Office | CP Name | CP Name | CP Name | CP Name | CP Name | CP Name | CP Name | CP Name | CP Name
MS Dynamic Proj Ops | MS Dynamic Proj Ops | MS Dynamic Proj Ops
Ref | Project Name | Client | CP Name | Contract Value (£) | Revenue Plan MTD (£) | Revenue Actual MTD (£) | Margin Forecast (%) | Opportunity Name | Pipeline Stage | Pipeline Value (£) | Repeat / New
GB01_P001074 | Project - UKPN - Cyber Resilience Roles T&M | UK Power Networks (Operations) Ltd | Sudhakar Nalla
GB01_P001021 | Project - UKPN - Income Management Mavis Faster Staging | UK Power Networks (Operations) Ltd | Sudhakar Nalla
GB01_P001073 | Project - UKPN - Nexus IMIB | UK Power Networks (Operations) Ltd | Sudhakar Nalla
0 | UKPN - Distance to Fault & CAS Pole Pilot | UK Power Networks (Operations) Ltd | Sudhakar Nalla
GB01_P001005 | Project - Eirgrid - Eirgrid PSSE to Power Factory | EirGrid plc | Rodrigo Merino
GB01_P001006 | Project - Eirgrid - Eirgird Product Specialist T&M | EirGrid plc | Rodrigo Merino
GB01_P001010 | Project - ENWL - SAP Projects | Electricity North West Limited | David Butcher
0 | ENWL - Project Manager - IT Resilience SMR - TnM | Electricity North West Limited | David Butcher
0 | WWU - Deed Digitalisation | Wales & West Utilities | Martin Ridley
0 | WWU - Service Suite Upgrade & MFT | Wales & West Utilities | Martin Ridley
GB01_P001075 | Project - WWU - Open Text | Wales & West Utilities | Martin Ridley
GB01_P001028 | Project - WWU- SAP Simplification Item - S/4 | Wales & West Utilities | Martin Ridley
GB01_P001026 | Project - WWU - S4 Resource and S4 Project Support New - FY26 | Wales & West Utilities | Martin Ridley
GB01_P001070 | Project - SGN - Dev Test FPP | Scotia Gas Networks Limited | Alex Pitcher
GB01_P001069 | Project - SGN - Dev Test T&M | Scotia Gas Networks Limited | Alex Pitcher

## 👥 Resource & Utilisation
👥 Resource & Utilisation ¦ Resource Manager-owned ¦ Updated Weekly
RESOURCE |  |  |  |  | HOURS (this week) |  |  |  | ASSIGNMENT
Portfolio Office | Resource Mgr | Resource Mgr | Resource Mgr | Resource Mgr | Resource Mgr | Resource Mgr | Resource Mgr | Resource Mgr | Resource Mgr | Resource Mgr | Resource Mgr
MS Dynamic Proj Ops | HR System* | HR System* | HR System* | HR System* | MS Dynamics Timesheet | MS Dynamics Timesheet | MS Dynamics Timesheet | Resource Report** | MS Dynamics Timesheet | Resource Report** | Resource Report**
Ref | Name | Practice | Region | Contract Hours/Wk | Leave Hours | Billable Hours | Non-Billable Hours | Utilisation % | Assigned Project(s) | Assignment Status | Notes
R001 | Danie Selvaraju | Apps & Development | UK | 37.5 | 0 | 35 | 2.5 | 93.33% | P001 | Assigned
R002 | Sam Lee | Data Intelligence & AI | UK | 37.5 | 0 | 30 | 7.5 | 80% | P002 | Assigned
R003 | Priya Patel | Data Intelligence & AI | UK | 37.5 | 0 | 37.5 | 0 | 100% | P003 | Assigned
R004 | Tom Hughes | Renewables & Engineering | UK | 37.5 | 7.5 | 25 | 5 | 83.33% | P004 | Assigned | Part week - annual leave Mon-Tue
R005 | Anna Chen | Cyber Security | UK | 37.5 | 0 | 37.5 | 0 | 100% | P005 | Assigned
R006 | James Obi | OT | UK | 37.5 | 0 | 30 | 7.5 | 80% | P006 | Assigned
R007 | Ben Nair | Data Intelligence & AI | India | 40 | 0 | 36 | 4 | 90% | P002, P003 | Assigned
R008 | Meera Sharma | Apps & Development | India | 40 | 0 | 40 | 0 | 100% | P001 | Assigned
R009 | Chris Tate | Renewables & Engineering | UK | 37.5 | 0 | 0 | 37.5 | 0% | Unassigned | Bench | Available for new project
R010 | Fatima Al-Hassan | Cyber Security | UK | 37.5 | 0 | 20 | 17.5 | 53.33% | P005 | Part-assigned | 50% capacity only - internal training
* Need to find out name of system / source?
** Assuming there is a spreadsheet or tool we use to manage resource / demand

## ⭐ Client Satisfaction
⭐ Client Satisfaction ¦ CP-owned ¦ Collected Monthly / At Milestone
Rate delivery 1–5: 5 = Exceeds expectations. 4 = Meets expectations. 3 = Mostly met. 2 = Below expectations. 1 = Significantly below.
Portfolio Office | Portfolio Office | Portfolio Office | CP | CP | CP | CP | CP
MS Dynamic Proj Ops | MS Dynamic Proj Ops | MS Dynamic Proj Ops | Client Sat Survey* | Client Sat Survey* | Client Sat Survey* | Client Sat Survey* | Client Sat Survey*
Ref | Project Name | Client | Date Collected | Score (1-5) | Client Comment | Collected By | Next Collection Due
GB01_P001074 | Project - UKPN - Cyber Resilience Roles T&M | UK Power Networks (Operations) Ltd | 2026-05-05 | 4
GB01_P001021 | Project - UKPN - Income Management Mavis Faster Staging | UK Power Networks (Operations) Ltd | 2026-04-28 | 4
GB01_P001073 | Project - UKPN - Nexus IMIB | UK Power Networks (Operations) Ltd | 2026-04-28 | 4
0 | UKPN - Distance to Fault & CAS Pole Pilot | UK Power Networks (Operations) Ltd | 2026-05-05 | 2
GB01_P001005 | Project - Eirgrid - Eirgrid PSSE to Power Factory | EirGrid plc | 2026-05-01 | 1 | No agreement with client re overall project status
GB01_P001006 | Project - Eirgrid - Eirgird Product Specialist T&M | EirGrid plc | 2026-04-27 | 4
GB01_P001010 | Project - ENWL - SAP Projects | Electricity North West Limited | 2026-05-06 | 4 | Stabilisation process in progress and on track
0 | ENWL - Project Manager - IT Resilience SMR - TnM | Electricity North West Limited | 2026-04-29 | 4
0 | WWU - Deed Digitalisation | Wales & West Utilities
0 | WWU - Service Suite Upgrade & MFT | Wales & West Utilities
GB01_P001075 | Project - WWU - Open Text | Wales & West Utilities
GB01_P001028 | Project - WWU- SAP Simplification Item - S/4 | Wales & West Utilities
GB01_P001026 | Project - WWU - S4 Resource and S4 Project Support New - FY26 | Wales & West Utilities
GB01_P001070 | Project - SGN - Dev Test FPP | Scotia Gas Networks Limited |  | 3
GB01_P001069 | Project - SGN - Dev Test T&M | Scotia Gas Networks Limited |  | 5